## 分类定义
大类 | 篇数 | 二级分类 | 预计修改量（篇数） | 预计修改时间（一个人完成所需工作日） | 定义
功能文档 | 217 |  |  |  | 功能文档 | 引擎运行时提供的能力，最终体现在游戏画面或行为里。判据：删掉它，游戏就少一个能力。
| 29 | └ UI·经典MornUI | 27 | 7 | IDE文档 | LayaAir-IDE 这个工具本身怎么用。判据：删掉它，游戏照跑，只是编辑变麻烦。
| 24 | └ UI·新版FairyGUI | 23 | 27 | 其他文档 | 既不是工具用法也不是引擎能力——发布流程、环境搭建、迁移对照、学习路线、站务说明。
| 13 | └ 动画 | 3 | 3
| 12 | └ 材质与Shader | 2 | 10
| 12 | └ 2D物理 | 12 | 7 | 备注
| 10 | └ 寻路导航 | 12 | 20 | 1 | 预计修改量为全量的多为查缺补漏，预计复杂度低，修改时间短
| 12 | └ 粒子与特效 | 5 | 10 | 2 | 预计修改时间为一人所需完成时间
| 11 | └ 网格与渲染 | 4 | 14 | 3 | 预计时间需根据相同文档类型修订速度以及内容复杂度来计算
| 10 | └ UI·通用与编辑 | 3 | 10
| 9 | └ 场景与节点 | 4 | 16
| 9 | └ 3D物理 | 3 | 9
| 9 | └ 资源与加载 | 3 | 10
| 8 | └ 3D灯光与阴影 | 4 | 12
| 7 | └ 音视频 | 3 | 3
| 7 | └ 数学工具 | 0 | 0
| 6 | └ 2D灯光 | 6 | 5
| 5 | └ 设备接口与适配 | 5 | 10
| 5 | └ 2D显示对象 | 4 | 18
| 4 | └ 3D显示对象 | 3 | 13
| 4 | └ 蓝图 | 4 | 14
| 3 | └ 地图与瓦片 | 3 | 7
| 3 | └ 其它功能 | 0 | 0
| 2 | └ 性能优化 | 1 | 5
| 2 | └ 网络通信 | 2 | 5
| 1 | └ 相机 | 1 | 3
IDE文档 | 36
| 9 | └ 项目设置 | 9 | 3
| 8 | └ 插件与包管理 | 8 | 3
| 7 | └ 面板 | 7 | 10
| 5 | └ 项目与工程管理 | 1 | 3
| 4 | └ 界面与交互 | 0 | 0
| 3 | └ 自定义组件开发 | 0 | 0
其他文档 | 82
| 41 | └ 构建与发布 | 17 | 10
| 11 | └ 学习路线 | 2 | 5
| 10 | └ Unity导出插件 | 0 | 0
| 9 | └ 环境与工具链 | 4 | 5
| 7 | └ 站务与总览 | 2 | 5
| 3 | └ 迁移与对照 | 1 | 1
| 1 | └ 第三方库 | 0 | 0
总计 |  |  | 188 | 283

## 功能文档
二级分类 | 文档名 | 链接
UI·经典MornUI | 按钮组件Button | src/content/docs/IDE/uiEditor/uiComponent/Button/index.md
UI·经典MornUI | 垂直布局VBox | src/content/docs/IDE/uiEditor/uiComponent/VBox/index.md
UI·经典MornUI | 垂直滚动条VScrollBar | src/content/docs/IDE/uiEditor/uiComponent/VScrollBar/index.md
UI·经典MornUI | 垂直滑动条VSlider | src/content/docs/IDE/uiEditor/uiComponent/VSlider/index.md
UI·经典MornUI | 单选框组RadioGroup | src/content/docs/IDE/uiEditor/uiComponent/RadioGroup/index.md
UI·经典MornUI | 单选框Radio | src/content/docs/IDE/uiEditor/uiComponent/Radio/index.md
UI·经典MornUI | 导航标签组Tab | src/content/docs/IDE/uiEditor/uiComponent/Tab/index.md
UI·经典MornUI | 导航容器ViewStack | src/content/docs/IDE/uiEditor/uiComponent/ViewStack/index.md
UI·经典MornUI | 多行文本TextArea | src/content/docs/IDE/uiEditor/uiComponent/TextArea/index.md
UI·经典MornUI | 多选框CheckBox | src/content/docs/IDE/uiEditor/uiComponent/CheckBox/index.md
UI·经典MornUI | 进度条ProgressBar | src/content/docs/IDE/uiEditor/uiComponent/ProgressBar/index.md
UI·经典MornUI | 开放数据域 | src/content/docs/IDE/uiEditor/uiComponent/OpenDataContextView/index.md
UI·经典MornUI | 列表组件List | src/content/docs/IDE/uiEditor/uiComponent/List/index.md
UI·经典MornUI | 面板容器Panel | src/content/docs/IDE/uiEditor/uiComponent/Panel/index.md
UI·经典MornUI | 取色器ColorPicker | src/content/docs/IDE/uiEditor/uiComponent/ColorPicker/index.md
UI·经典MornUI | 容器组件Box | src/content/docs/IDE/uiEditor/uiComponent/Box/index.md
UI·经典MornUI | 输入文本TextInput | src/content/docs/IDE/uiEditor/uiComponent/TextInput/index.md
UI·经典MornUI | 树状列表Tree | src/content/docs/IDE/uiEditor/uiComponent/Tree/index.md
UI·经典MornUI | 水平布局HBox | src/content/docs/IDE/uiEditor/uiComponent/HBox/index.md
UI·经典MornUI | 水平滚动条HScrollBar | src/content/docs/IDE/uiEditor/uiComponent/HScrollBar/index.md
UI·经典MornUI | 水平滑动条HSlider | src/content/docs/IDE/uiEditor/uiComponent/HSlider/index.md
UI·经典MornUI | 图像组件Image | src/content/docs/IDE/uiEditor/uiComponent/Image/index.md
UI·经典MornUI | 位图切片Clip | src/content/docs/IDE/uiEditor/uiComponent/Clip/index.md
UI·经典MornUI | 下拉框ComboBox | src/content/docs/IDE/uiEditor/uiComponent/ComboBox/index.md
UI·经典MornUI | 显示文本Label | src/content/docs/IDE/uiEditor/uiComponent/Label/index.md
UI·经典MornUI | 选项框概览 | src/content/docs/IDE/uiEditor/uiComponent/optionBox/index.md
UI·经典MornUI | 字体切片FontClip | src/content/docs/IDE/uiEditor/uiComponent/FontClip/index.md
UI·经典MornUI | UI组件基础使用与构成 | src/content/docs/IDE/uiEditor/uiComponent/index.md
UI·经典MornUI | UI组件资源命名规则 | src/content/docs/IDE/uiEditor/uiComponent/namingRule/index.md
UI·新版FairyGUI | 按钮GButton | src/content/docs/IDE/uiEditor/FairyGUI/GButton/index.md
UI·新版FairyGUI | 布局容器GBox | src/content/docs/IDE/uiEditor/FairyGUI/GBox/index.md
UI·新版FairyGUI | 布局容器layout | src/content/docs/IDE/uiEditor/FairyGUI/layout/index.md
UI·新版FairyGUI | 窗口GWindow | src/content/docs/IDE/uiEditor/FairyGUI/GWindow/index.md
UI·新版FairyGUI | 动画GMovieClip | src/content/docs/IDE/uiEditor/FairyGUI/GMovieClip/index.md
UI·新版FairyGUI | 根节点与弹出GRoot | src/content/docs/IDE/uiEditor/FairyGUI/Groot/index.md
UI·新版FairyGUI | 关联系统relation | src/content/docs/IDE/uiEditor/FairyGUI/relation/index.md
UI·新版FairyGUI | 滚动条GScrollBar | src/content/docs/IDE/uiEditor/FairyGUI/GScrollBar/index.md
UI·新版FairyGUI | 滚动支持scroller | src/content/docs/IDE/uiEditor/FairyGUI/scroller/index.md
UI·新版FairyGUI | 国际化i18n | src/content/docs/IDE/uiEditor/FairyGUI/i18n/index.md
UI·新版FairyGUI | 滑动条GSlider | src/content/docs/IDE/uiEditor/FairyGUI/GSlider/index.md
UI·新版FairyGUI | 进度条GProgressBar | src/content/docs/IDE/uiEditor/FairyGUI/GProgressBar/index.md
UI·新版FairyGUI | 精灵GWidget | src/content/docs/IDE/uiEditor/FairyGUI/GWidget/index.md
UI·新版FairyGUI | 控制器Controller | src/content/docs/IDE/uiEditor/FairyGUI/controller/index.md
UI·新版FairyGUI | 列表GList | src/content/docs/IDE/uiEditor/FairyGUI/GList/index.md
UI·新版FairyGUI | 面板容器GPanel | src/content/docs/IDE/uiEditor/FairyGUI/GPanel/index.md
UI·新版FairyGUI | 输入文本GTextInput | src/content/docs/IDE/uiEditor/FairyGUI/GTextInput/index.md
UI·新版FairyGUI | 树GTree | src/content/docs/IDE/uiEditor/FairyGUI/GTree/index.md
UI·新版FairyGUI | 图片GImage | src/content/docs/IDE/uiEditor/FairyGUI/GImage/index.md
UI·新版FairyGUI | 文本GTextField | src/content/docs/IDE/uiEditor/FairyGUI/GTextField/index.md
UI·新版FairyGUI | 下拉框GComboBox | src/content/docs/IDE/uiEditor/FairyGUI/GComboBox/index.md
UI·新版FairyGUI | 装载器GLoader | src/content/docs/IDE/uiEditor/FairyGUI/GLoader/index.md
UI·新版FairyGUI | FairyGUI架构概述 | src/content/docs/IDE/uiEditor/FairyGUI/index.md
UI·新版FairyGUI | Selection支持 | src/content/docs/IDE/uiEditor/FairyGUI/selection/index.md
动画 | 2D动画组件Animator2D | src/content/docs/IDE/Component/2D/2DAnimation/Animator2D/index.md
动画 | 3D模型与动画的导入使用 | src/content/docs/3D/useModel/index.md
动画 | 动画烘焙详解 | src/content/docs/IDE/animationEditor/aniBake/index.md
动画 | 动画节点Animation | src/content/docs/2D/displayObject/Animation/index.md
动画 | 动画状态机详解 | src/content/docs/IDE/animationEditor/aniController/index.md
动画 | 反向动力学ChainsIK | src/content/docs/IDE/Component/3DAnimation/ChainsIK/index.md
动画 | 骨骼动画概览 | src/content/docs/IDE/uiEditor/uiComponent/skeleton/index.md
动画 | 骨骼约束BoneConstraints | src/content/docs/IDE/Component/3DAnimation/BoneConstraints/index.md
动画 | 内置骨骼动画 | src/content/docs/IDE/uiEditor/uiComponent/skeleton/sk/index.md
动画 | 时间轴动画编辑详解 | src/content/docs/IDE/animationEditor/timelineGUI/index.md
动画 | 序列帧动画FrameAnimation | src/content/docs/IDE/Component/2D/2DAnimation/FrameAnimation/index.md
动画 | Spine3D渲染器 | src/content/docs/IDE/Component/3DRender/Spine3DRenderer/index.md
动画 | Spine渲染器Spine2DRenderNode | src/content/docs/IDE/Component/2D/2DRender/Spine2DRenderNode/index.md
材质与Shader | 不受光材质Unlit | src/content/docs/IDE/assets/lmat/Unlit/index.md
材质与Shader | 布林冯材质BlinPhong | src/content/docs/IDE/assets/lmat/BlinPhong/index.md
材质与Shader | 材质资源总览 | src/content/docs/IDE/assets/lmat/index.md
材质与Shader | 后处理 | src/content/docs/3D/advanced/PostProcessing/index.md
材质与Shader | 基于物理的渲染材质PBR | src/content/docs/IDE/assets/lmat/PBR/index.md
材质与Shader | 基于物理渲染材质glTF | src/content/docs/IDE/assets/lmat/glTFPBR/index.md
材质与Shader | 计算着色器ComputeShader | src/content/docs/basics/WebGPU/ComputeShader/index.md
材质与Shader | 天空材质Sky | src/content/docs/IDE/assets/lmat/Sky/index.md
材质与Shader | 拖尾材质Trail | src/content/docs/IDE/assets/lmat/Trail/index.md
材质与Shader | 一篇学会自定义Shader | src/content/docs/3D/advanced/customShader/index.md
材质与Shader | 自定义2D着色器 | src/content/docs/2D/advanced/customShader/index.md
材质与Shader | IDE的材质属性 | src/content/docs/IDE/materialEditor/index.md
2D物理 | 2D刚体RigidBody | src/content/docs/IDE/Component/physics2D/rigidBody/index.md
2D物理 | 2D静态碰撞器 | src/content/docs/IDE/Component/physics2D/staticCollider/index.md
2D物理 | 2D物理 | src/content/docs/IDE/physicsEditor/physics2D/index.md
2D物理 | 齿轮关节 | src/content/docs/IDE/Component/physics2D/gearJoint/index.md
2D物理 | 焊接关节 | src/content/docs/IDE/Component/physics2D/weldJoint/index.md
2D物理 | 滑轮关节 | src/content/docs/IDE/Component/physics2D/pulleyJoint/index.md
2D物理 | 距离关节 | src/content/docs/IDE/Component/physics2D/distanceJoint/index.md
2D物理 | 轮子关节 | src/content/docs/IDE/Component/physics2D/wheelJoint/index.md
2D物理 | 马达关节 | src/content/docs/IDE/Component/physics2D/motorJoint/index.md
2D物理 | 平移关节 | src/content/docs/IDE/Component/physics2D/PrismaticJoint/index.md
2D物理 | 鼠标关节 | src/content/docs/IDE/Component/physics2D/mouseJoint/index.md
2D物理 | 旋转关节 | src/content/docs/IDE/Component/physics2D/revoluteJoint/index.md
粒子与特效 | 2D粒子编辑器 | src/content/docs/IDE/particleEditor2D/index.md
粒子与特效 | 3D粒子编辑器 | src/content/docs/IDE/particleEditor3D/index.md
粒子与特效 | 代码篇 | src/content/docs/vfx-graph/code.md
粒子与特效 | 概念篇 | src/content/docs/vfx-graph/concepts.md
粒子与特效 | 粒子材质ParticleShuriken | src/content/docs/IDE/assets/lmat/ParticleShuriken/index.md
粒子与特效 | 示例验证索引 | src/content/docs/vfx-graph/examples.md
粒子与特效 | 属性详解Block | src/content/docs/vfx-graph/block.md
粒子与特效 | 属性详解Context | src/content/docs/vfx-graph/context.md
粒子与特效 | 属性详解Operator | src/content/docs/vfx-graph/operator.md
粒子与特效 | 图级与组件 | src/content/docs/vfx-graph/graph-and-components.md
粒子与特效 | IDE操作流程 | src/content/docs/vfx-graph/ide-workflow.md
粒子与特效 | VFX Graph教学文档集 | src/content/docs/vfx-graph/index.md
网格与渲染 | 2D拖尾Trail2DRender | src/content/docs/IDE/Component/2D/2DRender/Trail2DRender/index.md
网格与渲染 | 2D网格渲染器Mesh2DRender | src/content/docs/IDE/Component/2D/2DRender/Mesh2DRender/index.md
网格与渲染 | 2D像素线Line2DRender | src/content/docs/IDE/Component/2D/2DRender/Line2DRender/index.md
网格与渲染 | 静态合批StaticBatchVolume | src/content/docs/IDE/Component/StaticBatchVolume/index.md
网格与渲染 | 拖尾旧Trail | src/content/docs/IDE/Component/Trail/index.md
网格与渲染 | 拖尾渲染器TrailRenderer | src/content/docs/IDE/Component/3DRender/TrailRenderer/index.md
网格与渲染 | 网格过滤器MeshFilter | src/content/docs/IDE/Component/Mesh/MeshFilter/index.md
网格与渲染 | 网格渲染器MeshRenderer | src/content/docs/IDE/Component/Mesh/MeshRenderer/index.md
网格与渲染 | 网格Mesh index | src/content/docs/IDE/Component/Mesh/index.md
网格与渲染 | 像素线PixelLine | src/content/docs/IDE/Component/PixelLine/index.md
网格与渲染 | LOD | src/content/docs/IDE/Component/LOD/index.md
寻路导航 | 2D导航代理Nav2DAgent | src/content/docs/IDE/Component/2D/navMesh/Nav2DAgent/index.md
寻路导航 | 2D导航网格表面 | src/content/docs/IDE/Component/2D/navMesh/NavMesh2DSurface/index.md
寻路导航 | 2D寻路index | src/content/docs/IDE/Component/2D/navMesh/index.md
寻路导航 | 3D导航代理NavAgent | src/content/docs/IDE/Component/navMesh/NavAgent/index.md
寻路导航 | 3D寻路index | src/content/docs/IDE/Component/navMesh/index.md
寻路导航 | 导航区域链接NavMeshLink | src/content/docs/IDE/Component/navMesh/NavMeshLink/index.md
寻路导航 | 导航障碍物NavMeshObstacles | src/content/docs/IDE/Component/navMesh/NavMeshObstacles/index.md
寻路导航 | 动态导航表面NavMeshModifileSurface | src/content/docs/IDE/Component/navMesh/NavMeshModifileSurface/index.md
寻路导航 | 动态区域体积NavMeshModifierVolume | src/content/docs/IDE/Component/navMesh/NavMeshModifierVolume/index.md
寻路导航 | 静态导航表面NavMesh3DSurface | src/content/docs/IDE/Component/navMesh/NavMesh3DSurface/index.md
UI·通用与编辑 | 2D区域Area2D | src/content/docs/IDE/uiEditor/area2d/index.md
UI·通用与编辑 | 2D相机Camera2D | src/content/docs/IDE/uiEditor/area2d/camera2d/index.md
UI·通用与编辑 | 弹窗视图Dialog | src/content/docs/IDE/uiEditor/dialog/index.md
UI·通用与编辑 | 后期处理PostProcess | src/content/docs/IDE/uiEditor/postProcess/index.md
UI·通用与编辑 | 绘制图形graphics | src/content/docs/IDE/uiEditor/graphics/index.md
UI·通用与编辑 | 混合使用3D | src/content/docs/IDE/uiEditor/use3D/index.md
UI·通用与编辑 | 使用3D UI | src/content/docs/IDE/uiEditor/3dui/index.md
UI·通用与编辑 | 纹理压缩textureCompress | src/content/docs/IDE/uiEditor/texturecompress/index.md
UI·通用与编辑 | UI小部件 | src/content/docs/IDE/uiEditor/widgets/index.md
UI·通用与编辑 | UI运行时 | src/content/docs/IDE/uiEditor/runtime/index.md
场景与节点 | 2D内置组件index | src/content/docs/IDE/Component/2D/index.md
场景与节点 | 3D场景环境设置 | src/content/docs/IDE/sceneEditor/environment/index.md
场景与节点 | 场景管理 | src/content/docs/basics/common/scene/index.md
场景与节点 | 定时器Timer | src/content/docs/basics/common/timer/index.md
场景与节点 | 对象池Pool | src/content/docs/basics/common/pool/index.md
场景与节点 | 缓动Tween | src/content/docs/basics/common/tween/index.md
场景与节点 | 节点管理Node | src/content/docs/basics/common/node/index.md
场景与节点 | 实体组件系统ECS | src/content/docs/basics/common/component/index.md
场景与节点 | 事件管理 | src/content/docs/basics/common/event/index.md
3D物理 | 3D刚体Rigidbody3D | src/content/docs/IDE/Component/physics3D/Rigidbody3D/index.md
3D物理 | 3D静态碰撞器 | src/content/docs/IDE/Component/physics3D/PhysicsCollider/index.md
3D物理 | 3D物理系统 | src/content/docs/IDE/physicsEditor/physics3D/index.md
3D物理 | 弹簧约束SpringConstraint | src/content/docs/IDE/Component/physics3D/SpringConstraint/index.md
3D物理 | 固定约束FixedConstraint | src/content/docs/IDE/Component/physics3D/FixedConstraint/index.md
3D物理 | 角色控制器 | src/content/docs/IDE/Component/physics3D/CharacterController/index.md
3D物理 | 铰链约束HingeConstraint | src/content/docs/IDE/Component/physics3D/HingeConstraint/index.md
3D物理 | 可配置约束ConfigurableConstraint | src/content/docs/IDE/Component/physics3D/ConfigurableConstraint/index.md
3D物理 | 自定义物理引擎库 | src/content/docs/3D/advanced/customPhysicsEngine/index.md
资源与加载 | 动态图集DynamicAtlasManager | src/content/docs/2D/dynamicAtlas/index.md
资源与加载 | 脚本集定义 | src/content/docs/IDE/assets/bundledef/index.md
资源与加载 | 立方体贴图Cubemap | src/content/docs/IDE/assets/Cubemap/index.md
资源与加载 | 模型导入设置 | src/content/docs/IDE/assets/model/index.md
资源与加载 | 纹理资源设置说明 | src/content/docs/IDE/assets/texture/index.md
资源与加载 | 预制体模块 | src/content/docs/IDE/assets/prefab/index.md
资源与加载 | 资源加载Loader | src/content/docs/basics/common/loader/index.md
资源与加载 | 自动图集配置 | src/content/docs/IDE/assets/atlascfg/index.md
资源与加载 | Unity资源导出插件导读 | src/content/docs/3D/advanced/Unity/index.md
3D灯光与阴影 | 3D灯光与阴影 | src/content/docs/3D/Light/index.md
3D灯光与阴影 | 3D点光源 | src/content/docs/IDE/Component/3DLight/PointLight/index.md
3D灯光与阴影 | 3D方向光 | src/content/docs/IDE/Component/3DLight/DirectionLight/index.md
3D灯光与阴影 | 3D聚光灯 | src/content/docs/IDE/Component/3DLight/SpotLight/index.md
3D灯光与阴影 | 3D区域光 | src/content/docs/IDE/Component/3DLight/AreaLight/index.md
3D灯光与阴影 | 3D阴影 | src/content/docs/IDE/Component/3DLight/Shadow/index.md
3D灯光与阴影 | 反射探针ReflectionProbe | src/content/docs/IDE/Component/ReflectionProbe/index.md
3D灯光与阴影 | 体积GI VolumetricGI | src/content/docs/IDE/Component/VolumetricGI/index.md
音视频 | 多媒体组件index | src/content/docs/IDE/Component/Media/index.md
音视频 | 使用音频 | src/content/docs/basics/common/device/media/index.md
音视频 | 视频 | src/content/docs/basics/common/device/video/index.md
音视频 | 视频播放VideoPlayer | src/content/docs/IDE/Component/Media/VideoPlayer/index.md
音视频 | 视频节点VideoNode | src/content/docs/2D/displayObject/VideoNode/index.md
音视频 | 音频播放SoundPlayer | src/content/docs/IDE/Component/Media/SoundPlayer/index.md
音视频 | 音频节点SoundNode | src/content/docs/2D/displayObject/SoundNode/index.md
数学工具 | 贝塞尔曲线 | src/content/docs/basics/common/math/bezierCurve/index.md
数学工具 | 插值Interpolation | src/content/docs/basics/common/math/interpolation/index.md
数学工具 | 矩阵Matrix4 | src/content/docs/basics/common/math/matrix4/index.md
数学工具 | 射线Ray | src/content/docs/basics/common/math/ray/index.md
数学工具 | 四元数Quaternion | src/content/docs/basics/common/math/quaternion/index.md
数学工具 | 随机数Random | src/content/docs/basics/common/math/random/index.md
数学工具 | 向量Vector | src/content/docs/basics/common/math/vector234/index.md
2D灯光 | 2D灯光与网格BaseLight2D | src/content/docs/IDE/Component/2D/BaseLight2D/index.md
2D灯光 | 2D方向光 | src/content/docs/IDE/Component/2D/DirectionLight2D/index.md
2D灯光 | 2D光遮挡器 | src/content/docs/IDE/Component/2D/LightOccluder2D/index.md
2D灯光 | 2D精灵光 | src/content/docs/IDE/Component/2D/SpriteLight2D/index.md
2D灯光 | 2D聚光灯 | src/content/docs/IDE/Component/2D/SpotLight2D/index.md
2D灯光 | 2D自由形态光 | src/content/docs/IDE/Component/2D/FreeformLight2D/index.md
设备接口与适配 | 浏览器接口Browser | src/content/docs/basics/common/browser/index.md
设备接口与适配 | 屏幕适配 | src/content/docs/basics/common/adaptScreen/index.md
设备接口与适配 | 使用百度地图 | src/content/docs/basics/common/device/baiduMap/index.md
设备接口与适配 | 陀螺仪加速计motion | src/content/docs/basics/common/device/motion/index.md
设备接口与适配 | Geolocation获位置 | src/content/docs/basics/common/device/geolocation/index.md
2D显示对象 | 多线程worker | src/content/docs/2D/useWorker/index.md
2D显示对象 | 基础文本Text | src/content/docs/2D/displayObject/Text/index.md
2D显示对象 | 精灵Sprite | src/content/docs/2D/displayObject/Sprite/index.md
2D显示对象 | 文本进阶使用 | src/content/docs/2D/advanced/useText/index.md
2D显示对象 | LayaAir和原生Dom | src/content/docs/2D/dom/index.md
3D显示对象 | 3D基础显示对象 | src/content/docs/3D/displayObject/index.md
3D显示对象 | 使用3D精灵Sprite3D | src/content/docs/3D/Sprite3D/index.md
3D显示对象 | CommandBuffer文档 | src/content/docs/3D/advanced/CommandBuffer/index.md
3D显示对象 | WebXR使用说明 | src/content/docs/3D/WebXR/index.md
蓝图 | 程序蓝图2D | src/content/docs/IDE/Component/2D/BlueprintScript/index.md
蓝图 | 程序蓝图3D | src/content/docs/IDE/Component/BlueprintScript/index.md
蓝图 | 程序蓝图资源 | src/content/docs/IDE/assets/blueprint/BlueprintScript/index.md
蓝图 | Shader蓝图旧 | src/content/docs/IDE/assets/blueprint/shaderBlueprint/index.md
地图与瓦片 | 使用TiledMap地图 | src/content/docs/2D/TiledMap/index.md
地图与瓦片 | 瓦片地图层TileMapLayer | src/content/docs/IDE/Component/2D/TileMapLayer/index.md
地图与瓦片 | 瓦片地图TileSet | src/content/docs/IDE/assets/TileSet/index.md
其它功能 | 2D基础概念 | src/content/docs/basics/common/basicConcepts/index.md
其它功能 | 3D变换 | src/content/docs/basics/3D/Transform/index.md
其它功能 | 3D概念入门 | src/content/docs/basics/3D/beginner/index.md
性能优化 | 2D性能优化 | src/content/docs/2D/performanceOptimization/index.md
性能优化 | 3D性能优化 | src/content/docs/3D/advanced/performanceOptimization/index.md
网络通信 | HTTP通信 | src/content/docs/basics/common/network/HTTP/index.md
网络通信 | WebSocket通信 | src/content/docs/basics/common/network/WebSocket/index.md
相机 | 一篇学会使用3D摄像机 | src/content/docs/3D/Camera/index.md

## IDE文档
二级分类 | 文档名 | 链接
项目设置 | 脚本编译 | src/content/docs/basics/IDE/projectSettings/scriptCompiler/index.md
项目设置 | 启动页配置 | src/content/docs/basics/IDE/projectSettings/startPage/index.md
项目设置 | 物理系统项目设置 | src/content/docs/basics/IDE/projectSettings/physicalSystem/index.md
项目设置 | 引擎模块 | src/content/docs/basics/IDE/projectSettings/engineModule/index.md
项目设置 | 引擎统计信息 | src/content/docs/basics/IDE/projectSettings/statistics/index.md
项目设置 | 预览服务 | src/content/docs/basics/IDE/projectSettings/previewServer/index.md
项目设置 | 预设值 | src/content/docs/basics/IDE/projectSettings/preset/index.md
项目设置 | 运行配置 | src/content/docs/basics/IDE/projectSettings/runConfig/index.md
项目设置 | WebGPU启用配置 | src/content/docs/basics/IDE/projectSettings/webGPU/index.md
插件与包管理 | 3D骨骼动作烘焙插件 | src/content/docs/IDE/layapackage/Layabox/BakeAnimation/index.md
插件与包管理 | 包管理器与资源包导入 | src/content/docs/IDE/layapackage/pluginImport/index.md
插件与包管理 | 性能分析插件 | src/content/docs/IDE/layapackage/enterprise/performanceAnalysis/index.md
插件与包管理 | 资源包导出与提交至商店 | src/content/docs/IDE/layapackage/exportToStore/index.md
插件与包管理 | CPU粒子系统 | src/content/docs/IDE/layapackage/enterprise/cpuParticle/index.md
插件与包管理 | IDE插件开发说明 | src/content/docs/IDE/layapackage/plug-in/index.md
插件与包管理 | LOD减面工具插件 | src/content/docs/IDE/layapackage/Layabox/LOD/index.md
插件与包管理 | Spine动画烘焙插件 | src/content/docs/IDE/layapackage/enterprise/spineBake/index.md
面板 | 层级面板说明 | src/content/docs/basics/IDE/Hierarchy/index.md
面板 | 场景面板 | src/content/docs/basics/IDE/Scene/index.md
面板 | 属性设置面板说明 | src/content/docs/basics/IDE/Inspector/index.md
面板 | 项目资源面板说明 | src/content/docs/basics/IDE/assets/index.md
面板 | 预览运行面板说明 | src/content/docs/basics/IDE/Game/index.md
面板 | 资源依赖面板 | src/content/docs/basics/IDE/AssetDependency/index.md
面板 | IDE主要模块概述 | src/content/docs/basics/IDE/GUI/index.md
项目与工程管理 | 创建新项目 | src/content/docs/basics/IDE/createNewProject/index.md
项目与工程管理 | 开发流程:Hello World | src/content/docs/basics/IDE/helloWorld/index.md
项目与工程管理 | 项目工程目录说明 | src/content/docs/basics/IDE/projecFolders/index.md
项目与工程管理 | 项目启动入口说明 | src/content/docs/basics/IDE/entry/index.md
项目与工程管理 | 引用第三方JS模块 | src/content/docs/basics/IDE/importJsLibrary/index.md
界面与交互 | 3D场景编辑基础交互 | src/content/docs/IDE/sceneEditor/basic/index.md
界面与交互 | 自定义IDE界面布局 | src/content/docs/basics/IDE/layouts/index.md
界面与交互 | IDE快捷键与鼠标交互操作大全 | src/content/docs/basics/IDE/shortcutKeyCombinations/index.md
界面与交互 | UI编辑器基础交互 | src/content/docs/IDE/uiEditor/basic/index.md
自定义组件开发 | 组件属性的代码使用 | src/content/docs/IDE/customComponent/componentProperties/index.md
自定义组件开发 | 组件装饰器标识详细说明 | src/content/docs/IDE/customComponent/decorators/index.md
自定义组件开发 | ECS系统组件脚本内置方法 | src/content/docs/IDE/customComponent/system/index.md

## 其他文档
二级分类 | 文档名 | 链接
构建与发布 | 抖音小游戏 | src/content/docs/released/miniGame/byteDance/index.md
构建与发布 | 反射二次开发 | src/content/docs/released/native/Secondary_Development/index.md
构建与发布 | 构建鸿蒙NEXT工程 | src/content/docs/released/Harmony/index.md
构建与发布 | 构建Linux工程 | src/content/docs/released/Linux/index.md
构建与发布 | 关于LocalStorage | src/content/docs/released/native/LocalStrorage/index.md
构建与发布 | 横竖屏设置 | src/content/docs/released/native/screen_orientation/index.md
构建与发布 | 鸿蒙真机调试JS | src/content/docs/released/Harmony/debug/index.md
构建与发布 | 接管鸿蒙后退键 | src/content/docs/released/native/OHOS_BackPress/index.md
构建与发布 | 接管Android后退键 | src/content/docs/released/native/Android_BackPress/index.md
构建与发布 | 命令行发布 | src/content/docs/released/commandLine/index.md
构建与发布 | 其他说明 | src/content/docs/released/native/Other_settings/index.md
构建与发布 | 启动页设置 | src/content/docs/released/native/SplashScreenSettings/index.md
构建与发布 | 嵌入字体 | src/content/docs/released/native/built_in_font/index.md
构建与发布 | 淘宝小游戏 | src/content/docs/released/miniGame/tbgame/index.md
构建与发布 | 通用发布 | src/content/docs/released/generalSetting/index.md
构建与发布 | 网络状态监听 | src/content/docs/released/native/network/index.md
构建与发布 | 微信小游戏 | src/content/docs/released/miniGame/wechat/index.md
构建与发布 | 微信Worker | src/content/docs/released/miniGame/wechat/Worker/index.md
构建与发布 | 小米快游戏 | src/content/docs/released/miniGame/xiaomi/index.md
构建与发布 | 小游戏发布总 | src/content/docs/released/miniGame/index.md
构建与发布 | 原生与JS通信 | src/content/docs/released/native/platform_communication/index.md
构建与发布 | 支付宝小游戏 | src/content/docs/released/miniGame/alipaygame/index.md
构建与发布 | 资源更新zipUpdate | src/content/docs/released/native/zipUpdate/index.md
构建与发布 | Android apk发布 | src/content/docs/released/Android/index.md
构建与发布 | Android文件扩展 | src/content/docs/released/native/apk_expansion/index.md
构建与发布 | Android真机调试JS | src/content/docs/released/Android/debug/index.md
构建与发布 | APP扫码运行器 | src/content/docs/released/native/previewRunner/index.md
构建与发布 | CrazyGames发布 | src/content/docs/released/CrazyGames/index.md
构建与发布 | iOS构建发布 | src/content/docs/released/iOS/index.md
构建与发布 | LayaDCC2.0工具 | src/content/docs/released/native/LayaDcc_Tool/index.md
构建与发布 | LayaNative入口说明 | src/content/docs/released/native/native_index/index.md
构建与发布 | LayaNative文件系统 | src/content/docs/released/native/FileSystem/index.md
构建与发布 | LayaNative综述 | src/content/docs/released/native/LayaNative_Introduction/index.md
构建与发布 | OPPO小游戏 | src/content/docs/released/miniGame/OPPO/index.md
构建与发布 | Poki发布 | src/content/docs/released/Poki/index.md
构建与发布 | Steam扩展实例 | src/content/docs/released/Windows/steam/index.md
构建与发布 | vivo小游戏 | src/content/docs/released/miniGame/vivo/index.md
构建与发布 | Web单文件发布 | src/content/docs/released/singleWeb/index.md
构建与发布 | Web发布 | src/content/docs/released/web/index.md
构建与发布 | Windows发布 | src/content/docs/released/Windows/index.md
构建与发布 | Windows扩展 | src/content/docs/released/Windows/extension/index.md
学习路线 | 2D入门方向 | src/content/docs/guides/roadmap/beginner/path-2d.mdx
学习路线 | 3D入门方向 | src/content/docs/guides/roadmap/beginner/path-3d.mdx
学习路线 | 程序进阶路线 | src/content/docs/guides/roadmap/intermediate/index.md
学习路线 | 程序新手路线 | src/content/docs/guides/roadmap/beginner/index.mdx
学习路线 | 创建第一个项目 | src/content/docs/guides/roadmap/beginner/first-project.mdx
学习路线 | 美术路线 | src/content/docs/guides/roadmap/artist/index.md
学习路线 | 掌握核心概念 | src/content/docs/guides/roadmap/beginner/core-concepts.mdx
学习路线 | 准备环境与语言 | src/content/docs/guides/roadmap/beginner/prepare.mdx
学习路线 | 自检与下一步 | src/content/docs/guides/roadmap/beginner/checklist.mdx
学习路线 | AI开发路线 | src/content/docs/guides/roadmap/AI/index.md
学习路线 | Unity/Cocos迁移路线 | src/content/docs/guides/roadmap/migration/index.md
Unity导出插件 | 2D精灵导出 | src/content/docs/unity-plugin/sprite-2d.mdx
Unity导出插件 | 安装与导出窗口介绍 | src/content/docs/unity-plugin/install.mdx
Unity导出插件 | 材质与Shader导出 | src/content/docs/unity-plugin/material-shader.mdx
Unity导出插件 | 动画导出 | src/content/docs/unity-plugin/animation.mdx
Unity导出插件 | 粒子系统导出 | src/content/docs/unity-plugin/particle.mdx
Unity导出插件 | 网格导出 | src/content/docs/unity-plugin/mesh.mdx
Unity导出插件 | 疑似源码问题清单 | src/content/docs/unity-plugin/known-issues.mdx
Unity导出插件 | 整体导出流程 | src/content/docs/unity-plugin/overview.mdx
Unity导出插件 | 自定义Shader导出 | src/content/docs/unity-plugin/custom-shader.mdx
Unity导出插件 | Unity导出插件能力一览 | src/content/docs/unity-plugin/index.mdx
环境与工具链 | 初学者必读 | src/content/docs/basics/developmentEnvironment/index.md
环境与工具链 | 搭建开发环境 | src/content/docs/basics/developmentEnvironment/download/index.md
环境与工具链 | 如何阅读LayaAir的API | src/content/docs/basics/developmentEnvironment/API/index.md
环境与工具链 | 语言基础 | src/content/docs/basics/language/index.md
环境与工具链 | AI命令行工具LayaAir CLI | src/content/docs/basics/developmentEnvironment/CLI/index.md
环境与工具链 | AI协同开发环境 | src/content/docs/basics/developmentEnvironment/AIGC/index.md
环境与工具链 | DevTools调试工具 | src/content/docs/basics/DevTools/index.md
环境与工具链 | LayaAir MCP开发指南 | src/content/docs/basics/developmentEnvironment/IDE-MCP/index.md
环境与工具链 | LayaIdea使用说明 | src/content/docs/basics/developmentEnvironment/LayaIdea/index.md
站务与总览 | 可交互演示
站务与总览 | 文档使用说明 | src/content/docs/index.mdx
站务与总览 | 文档站写作与编辑指南 | src/content/docs/guides/authoring.mdx
站务与总览 | 引擎架构概述 | src/content/docs/basics/architecture/index.md
站务与总览 | LayaAir3引擎功能概述 | src/content/docs/basics/index.md
站务与总览 | LayaAir引擎介绍 | src/content/docs/services.md
站务与总览 | Unity导出能力一览演示版
迁移与对照 | 2.x升级3.x差异 | src/content/docs/basics/2.x-Upgrade/index.md
迁移与对照 | 为Unity开发者准备的指南 | src/content/docs/basics/UnityToLayaAir/index.md
迁移与对照 | Cocos资源导出插件 | src/content/docs/basics/developmentEnvironment/CocosToLayaAir/index.md
第三方库 | ProtocolBuffer通信 | src/content/docs/libs/Protobuf/index.md

## 细分优先级
名次 | 大类 | 细分分类 | 篇数 | 备注
1 | 功能文档 | UI 新版·FairyGUI | 23 | 7月27 改动其中一篇，作为ui功能改动的模板
2 | IDE文档 | 编辑面板 | 9 | 7月27 改动其中一篇，验证ide文档的工作流
3 | 功能文档 | 蓝图 | 4 | 7月27 改动shader蓝图，复杂任务试水
4 | 功能文档 | CommandBuffer | 1
5 | 功能文档 | 瓦片地图 | 3 | 7月27 重新整理结构，验证结构合理性 中等任务
6 | 功能文档 | 精灵与显示对象 | 3
7 | 功能文档 | 设备接口 | 4
8 | 功能文档 | 内置骨骼动画 | 3
9 | 功能文档 | 模型动画导入 | 1
10 | 功能文档 | 音频 | 3
11 | IDE文档 | 上手流程 | 1
12 | 功能文档 | 自定义物理引擎 | 1
13 | 功能文档 | LOD 与合批 | 2
14 | 功能文档 | WebXR | 1
15 | 功能文档 | 3D 阴影 | 2
16 | 功能文档 | 物理总览 | 1
17 | 功能文档 | 材质编辑 | 2
18 | 功能文档 | 性能优化 | 2
19 | 功能文档 | 序列帧动画 | 3
20 | 功能文档 | 原生 Dom | 1
21 | 功能文档 | 场景 | 2
22 | 功能文档 | 视频 | 3
23 | IDE文档 | 插件与包管理 | 8
24 | 功能文档 | 文本 | 2
25 | 功能文档 | 拖尾 | 3
26 | 功能文档 | 反射探针 | 1
27 | 功能文档 | 体积 GI | 1
28 | 功能文档 | UI 经典·MornUI | 26
29 | 功能文档 | 模块总览 | 2
30 | 功能文档 | 网格渲染 | 4
31 | 功能文档 | 3D 灯光 | 4
32 | 功能文档 | 2D 关节 | 9
33 | 功能文档 | 碰撞器 | 2
34 | 功能文档 | Worker 多线程 | 1
35 | IDE文档 | 界面布局 | 1
36 | 功能文档 | 屏幕适配 | 1
37 | IDE文档 | 项目与工程管理 | 4
38 | IDE文档 | 快捷键与交互 | 1
39 | 功能文档 | Unity 导出插件 | 1
40 | 功能文档 | 3D 变换 | 1
41 | 功能文档 | 3D 摄像机 | 1
42 | 功能文档 | 动画烘焙 | 1
43 | 功能文档 | 预制体 | 1
44 | 功能文档 | 时间轴动画 | 1
45 | 功能文档 | 粒子编辑器 | 2
46 | 功能文档 | 自定义 Shader | 3
47 | 功能文档 | UI 通用 | 2
48 | 功能文档 | 图集 | 2
49 | 功能文档 | 基础概念 | 2
50 | IDE文档 | 项目设置 | 9
51 | IDE文档 | 自定义组件开发 | 3
52 | 功能文档 | 纹理资源 | 2
53 | 功能文档 | 脚本集 | 1
54 | 功能文档 | 后处理 | 2
55 | 功能文档 | 内置材质 | 6
56 | 功能文档 | UI 导航菜单 | 2
57 | 功能文档 | 网络通信 | 2
58 | 功能文档 | 粒子材质 | 1
59 | 功能文档 | 线渲染 | 2
60 | 功能文档 | 矢量绘制 | 1
61 | 功能文档 | 动画状态机 | 2
62 | 功能文档 | IK 反向动力学 | 1
63 | 功能文档 | 3D 约束 | 4
64 | 功能文档 | 开放数据域 | 1
65 | 功能文档 | 2D 灯光 | 6
66 | 功能文档 | 刚体 | 2
67 | 功能文档 | 2D/3D 混用 | 2
68 | 功能文档 | VFX Graph | 9
69 | 功能文档 | 模型导入 | 1
70 | 功能文档 | 导航网格与代理 | 10
71 | 功能文档 | 角色控制器 | 1
72 | 功能文档 | Spine 骨骼动画 | 2
73 | 功能文档 | 音视频总览 | 1
74 | 功能文档 | 节点 | 1
75 | 功能文档 | 定时器 | 1
76 | 功能文档 | 事件 | 1
77 | 功能文档 | 对象池 | 1
78 | 功能文档 | 资源加载 | 1
79 | 功能文档 | Area2D 区域 | 1
80 | 功能文档 | 数学工具 | 7
81 | 功能文档 | 弹窗 | 1
82 | 功能文档 | 纹理压缩 | 1
83 | 功能文档 | 2D 相机 | 1
84 | 功能文档 | 缓动 Tween | 1
85 | 功能文档 | ECS 组件系统 | 1

## 第一周（7.27-8.2）
大类 | 细分分类 | 文档名 | 链接 | 改进需求 | 备注
修订
功能文档 | UI 新版·FairyGUI | 控制器Controller | src/content/docs/IDE/uiEditor/FairyGUI/controller/index.md |  | 改动fgui其中一篇，作为ui功能改动的模板
功能文档 | 蓝图 | Shader蓝图 | src/content/docs/IDE/assets/blueprint/shaderBlueprint/index.md |  | 复杂试水
IDE文档 | 编辑面板 | 场景面板 | src/content/docs/basics/IDE/Scene/index.md |  | 过于简陋 等同于重写 验证工作流
功能文档 | 瓦片地图 | 瓦片地图层TileMapLayer | src/content/docs/IDE/Component/2D/TileMapLayer/index.md |  | 修改结构 翻新文档 有些内容过时了
功能文档 | 瓦片地图 | 瓦片地图TileSet | src/content/docs/IDE/assets/TileSet/index.md
新增
其他文档 | 游戏美术 | 系列文档总览（首页） |  |  | 制定系列内容有什么，编写总览页
其他文档 | 新人入门 | 新手第一个2D游戏 |  |  | 策划此系列内容，提出总纲与demo需求